ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Center for development of East Planning Region

## Country background

The Beneficiary Country is a landlocked country on the Balkan Peninsula with an area of 25,713 km2 and population of 2,022,547 inhabitants (source: Census 2002), living in 84 municipalities.  It shares a border with Greece to the south, Bulgaria to the east, Serbia and Kosovo to the north, and Albania to the west. It has a diverse topography with high mountains and deep valleys, large and small natural lakes and picturesque rivers. The agricultural land covers 50% of the surface area while forests cover about one third from the country. The country has a diverse climate, with eight climatic regions.

The geographic location places the country at the crossroads of South-Eastern Europe, making it an important transit route for land traffic between Central Europe, the Aegean Sea, the Black Sea and the Adriatic Sea.

The country is 80% mountainous, rising to its highest point at Mountain Korab (peak 2,764 meters) with the lowest elevation (44 m) on the Vardar River at the border with Greece. Three climatic types overlap in the country: Mediterranean, moderately continental and mountainous, producing hot, dry summers and cold, snowy winters.

The hydrographical territory belongs to the following river basins: the Vardar river basin which gravitates towards the Aegean Sea, the Crn Drim river basin, comprising the Prespa and Ohrid lake basins, gravitates to the Adriatic Sea and the Strumica river basin gravitates to the Aegean Sea. A negligible part of the hydrographical territory drains to Danube river basin. There are three major natural lakes: Ohrid, Prespa and Dojran lakes

## Current situation in the sector

Over the period since achieving its independence, the Beneficiary Country has been striving to build a stable political and economic community, with a legal system able to facilitate rapid integration into the European Union and the wider international community. This primary strategic goal has given rise to sectoral targets, one of which is the establishment of efficient environmental protection measures in order to provide a basis for an improved quality of life.

The national legislation that deals with the issues of urban green spaces and green infrastructure is dealt with in the following laws: the Law on Urban Greenery (Official Gazette of the Republic of Moldova, No. 11/2018), the Law on Urban Planning (Official Gazette of the RSM, No. 32/ 2020), as well as their by-laws (regulations), the Law on communal activities ("Official Gazette of RSM" no. 302/20), the Law on building ("Official Gazette of RSM" no. 130/09, no. 111/ 23), the Law on Nature Protection ("Official Gazette of RSM" No. 67/04, 14/06, 84/07, 35/10, 47/11, 148/11, 59/12, 13/13, 163/13 , 41/14, 146/15, 39/16, 63/16, 113/18 and 151/21) the Law on Local Self-Government ("Official Gazette of RM" No. 5/2002), the Law on Public Enterprises, and the Law for the city of Skopje ("Official Gazette of the Republic of RM " No. 55/04 and 158/11) and the Expropriation Law ("Official Gazette of the Republic of RM " "Official Gazette of the Republic of RNM " No. 95/2012; 131/2012; 24/2013 27/2015; 192/2016; 111/2023.

The law on urban greenery, adopted in 2018, perceives the issues related to urban greenery in the most comprehensive way. Other laws address different aspects of urban green spaces. Thus, the Law on Urban Planning deals with the planning of land/space intended for greenery, the Law on Construction only with certain aspects of construction/creation of green spaces, and the Law on Communal Activities with the way of raising, maintaining and reconstructing green areas. Therefore, in the following, the basic legal solutions related to urban green areas will be presented.

It should be noted that in the past several attempts were made by various professional groups to pass a special law, which will apply exclusively to green areas (in cities, settlements, recreational areas), but unfortunately these attempts in the eighties and nineties years of the last century did not end with a comprehensive and functional law and by-laws that would regulate this area.

· Law on Urban Greenery

The Law on Greenery, adopted in 2016, is the first legal document that regulates numerous issues related to public green areas, from their planning to their maintenance, in an appropriate legal form. In 2018, the Law on Greenery was replaced by a new one - the Law on Urban Greenery (Annex 2). This Law regulates a number of aspects relevant to urban greenery, aiming to manage urban greenery in a way that will permanently preserve and increase its values. The Law regulates a number of aspects, from planning and defining standards and norms for planning and maintenance to establishing a system for managing and financing urban greenery. The law covers green areas within the planning scope of urban plans and other urban planning documentation, as well as green areas in the immediate surroundings of the city that are used as recreational or protective/protected areas.

Urban planning law

The Law systematically and hierarchically regulates urban planning and defines the organization, purpose, form and manner of use of space and land, as well as the spatial and functional conditions for the construction and use of the planned buildings. According to this, the land intended for greenery of different types is also determined. By this Law, urban greenery, i.e. urban green areas, are defined as "unbuilt construction land" and it is established that "unparceled construction land is construction land on which no construction plots have been formed, land that is limited by regulatory lines and that serves for general use, that is, for the construction of public spaces: streets, squares, infrastructures, urban greenery, etc.

From the perspective of the development of green infrastructure in urban areas, several strategic documents have been prepared in the Republic of North Macedonia so far at the local level, in which green infrastructure and its application in planning the development of cities is listed as one of the key activities for reducing pollution in the cities themselves. Unfortunately, the development of green infrastructure is at a very low level and it can be said that still green infrastructure as a tool for creating green cities is not recognized by planners and other stakeholders for urban development.

## Related programmes and other donor activities

A number of donors have supported environment sector in relation with the reduction of air pollution, climate change resilience and urban greening including the EU, USAID, World Bank Group, the Swiss Agency for Development and Cooperation and the UNDP.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

Enhancing protection and preservation of nature, biodiversity and green infrastructure, including in urban areas, and reducing all forms of pollution

The main objective is Cohesion through green solutions for urban areas in the cross-border region.

## Specific objective(s)

The specific objective of this contract is as follows:

- Making the green infrastructure as a main asset against biodiversity loss and climate change in urban areas, through joint strategic documents and innovative tools

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

LOT 1 - Consultancy

Formulated:

- Joint Green Infrastructure Strategy (2025 – 2035) for East Planning Region and Gotse Delchev

- Action plan (2025 – 2030) for green infrastructure for Shtip

- Joint green cities concept for Shtip and Gotse Delchev

- Provided trainer (developed trainings curriculum, presentation and working materials, reports) for four trainings

LOT 2- Project events organization

- Organized two project press conferences

- Organized four trainings

- Organized four workshops

LOT 3 - Organization of campaign and visibility materials

- Designed and developed Campaign materials, video and audio

- Designed and printed visibility materials (400 sets, 3 banners and 14 info boards)

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- There are available experts for formulation of strategic documents.

- There are relevant persons interested in the planned trainings

- Sufficient flow of relevant information for the project implementation between the involved parties

## Risks

- Lack of sufficient information/data and delays in ensuring available documents, necessary for the implementation of the contract

# SCOPE OF THE WORK

## General

### Description of the assignment

LOT 1 Consultancy

The contract should support the Contracting Authority in creation of condition for development of the green infrastructure in the CB area. In the scope of this LOT, Consultant should Develop Joint Green Infrastructure Strategy (2025 – 2035) for East Planning Region and Gotse Delchev, Action plan for Municipality of Shtip and Green city Concept. All strategic documents should be developed in cooperation with Bulgarian experts who will be selected by the municipality of Gotse Delchev from the Republic of Bulgaria. The consultant will be responsible for the development of documents relating to the East Planning Region of Republic of North Macedonia and the Municipality of Shtip and the formulation of joint documents.

With the aim introduction of green infrastructure as a way of sustainably solving part of communal problems and creating green areas in cities and other settlements Capacity Building Programme for green infrastructure (GI) and green transition will be implemented in the frame of the project. Also, with the aim preparation of the relevant stakeholders to take a part in the process of formulation of strategic documents, two joint two trainings (topics: green infrastructure, Green urbanism - sustainable urban design, Green city – principles and Green transition of Cities) should be organized in Kocani and Stip. All trainings should be implemented in the frame of two full-days. The Consultant should provide trainers who will be responsible for conducting of trainings, preparation of training materials and exercises and preparation of reports from trainings.

LOT 2 Project events organization

Center for development of the East planning region intends to organise several events, on the different occasion during the implementation of the project “Transforming of urban sites with Green infrastructures “. The contractor should support the Centre for Development of the East Planning Region in overall process of implementation of the project through providing of relevant services necessary for organization of project events, including providing of adequate halls and audio equipment where the project events will be held, providing of catering, coffee breaks, joint diners and accommodations for project participants. A total of 4 two-day trainings will be held in Shtip and Kocani by two, two press conferences in Shtip, as well as 4 workshops in Shtip.

LOT 3 Organization of campaign and visibility materials

Center for development of the East planning region intends to organise several events, on the different occasion during the implementation of the project “Transforming of urban sites with Green infrastructures “. The Consultant should support the Centre for Development of the East Planning Region in overall process of implementation of the project trough design, pre-printing and printing of consumables for project events and project promotional materials. Also the Consultant should support Center in the implementation of project through design and implementation od  Public Campaign. Campaign should use standard methods (campaign materials, billboards, brochure, audio and video spots, campaign events, presentations).

### Geographical area to be covered

East Planning Region of North Macedonia and Municipality of Gotse Delcev Republic of Bulgaria

### Target groups

Local and regional public authorities, Infrastructure public service providers, NGO’s and other interested groups and general publics,

## Specific work

LOT 1

Activity 4.2.1.1 – Development of Joint Green Infrastructure Strategy (2025 – 2035) for East Planning Region and Gotse Delchev

The Consultant should develop Joint Green Infrastructure Strategy (2025 – 2035) for East Planning Region and Gotse Delchev as a first step in the process of creation of conditions for more intensive greening of urban and peri urban areas in CB region and green transition. This strategic document should serve as a road map for the municipalities to plan and build greener region. Consultant should set out the vision for green infrastructure in the CB region (East planning region and Gotse Delchev) and to determine how future investment in green infrastructure will be secured and where investment should be targeted. The strategy should: identifies the value of green infrastructure assets and reinforces and promotes the compelling case for infesting in them; identifies existing green infrastructure assets and partnership strengths on which strategy will be build; establishes the priorities for green infrastructure priorities; sets out existing and potential mechanisms to finance green infrastructure priorities; impels planning and housing policy and other practical work to support improvement in green infrastructure across East region and Gotse Delchev.  Consultant should develop this document in close cooperation with the consultant which will be selected by the Municipality of Gotse Delchev. In the frame of the process of development this strategy document an digital map of green areas should be developed for Stip. On the map beside green areas and street trees, green links of green areas will be identified and present on the map, so the local citizen can use this map for planning of walking through the areas with shadows and pleasant environment. Four one day workshops should be organized in the frame of the development process.

Activity 4.2.1.2 - Formulation of Action plan (2025 – 2030) for green infrastructure for Shtip

After the development of the Strategy for Green Infrastructure, Consultant should define the basic priorities in terms of which measure to implement where and how, through development of an Action Plan for the Municipalities of Shtip for a period of 5 years, for the period from 2025 to 2030. Action Plan should include consideration of strategic green infrastructure initiatives identified in the strategy, and also place-specific projects shaped through ongoing engagement with local community. With appropriate funding, these projects can offer considerable potential to strengthen the urban greening, where delivered in line with the principles highlighted in the Green Infrastructure strategy. Green infrastructure action plan should outline project partners approach to improving the city’s outdoor environment and provides details of a range of exciting short-, medium- and long-term projects to help create quality green infrastructure and improve sustainability in the tackled cities across the next five years and beyond. In the process of development of action plan one workshop should be organized.

Activity 4.2.1.3 - Development of Joint green cities concept for Shtip and Gotse Delchev

The Consultant should develop a common concept of a green city that will take into account the specifics of the CB region itself and that will serve as a guide for defining regional and local policies that strive to create a green future for the cities in the CB region. In the concept seven thematic areas including diverse elements and aspects should be taken in consideration like: Green Transport (promoting walking, cycling, efficient public transport, compactness and connectivity); Green Urban Agriculture (Producing, processing, distributing, and consuming food); Environmental Quality and Water Security (application of green practices to keep and/or improve the quality of water, air and soil quality), ICT and Green Technologies (telecommunication technologies and smart tools available to facilitate the use of public and private services); Green Buildings (introduction of use of low development impact practices in the construction of new buildings and in the retrofit of the existing building stocks); Greening Public Services ( energy efficiency and renewable energy practices used in the production of public services such as drinking water, wastewater, solid wastes, energy) and Green Infrastructure (Strategy formulations will be included). During the process of developing of concept a serial of on-line working meetings should be conducted, on which each tackled area should be discussed and formulated.

Activity 4.2.1.4 – Providing of expert for capacity building programme

In the frame of the project with the aim increasing capacity of the project target group following trainings and workshop should be organized in Stip and Kocani:

- Green infrastructure (2 days),

- Green urbanism - sustainable urban design (2 days),

- Green city – principles (2 days) and

- Green transition of Cities (2 days)

The Consultant should provide adequate trainers for each training and workshop mentioned above. The Consultant should develop a curriculum for the trainings and workshops mentioned above. Trainers should prepare the needed trainings materials for the proper organization of these events, to hold the workshops and trainings and to prepare report for each event.

Main goal is to explain the basics of the green infrastructure and green transition principles and measures. Each training will gather a total of 20 participants. The methodology for trainings should be based on interactive approach including lecturing, practical exercises and learning through interaction between the consultant and the trainings attendees.

LOT 2 Project events organization

In the frame of this LOT, the contractor should organize following project events:

Activity 4.2.2.1 Organization of press conferences

- Promotional press conferences in Stip

The Contractor should provide:

A hall for conducting of press conferences with audio equipment. Catering and coffee break for promotional press conference in Shtip for 50 participants

- Closing press conferences in Shtip

The Contractor should provide Catering + coffee break for closing promotional event in Shtip for 50 participants on the location where the event will be held.

Activity 4.2.2.2 Organization of trainings

- Four Trainings (duration 2 days each)

    - Two trainings should be organized in Shtip

    - Two trainings should be organized in Kocani

The Contractor should provide:

For the trainings in Stip - Accommodation for 20 participants in single room for one night on the base of HB in Shtip; A hall with appropriate audio equipment for conducting of Training for approximately 20 people; one daily coffee breaks (complete coffee, mineral water, juice and cookies) for all participants in workshops (20 participants) and catering – lunch with included one non-alcoholic beverages per participant.

For the trainings in Kocani - Accommodation for 20 participants in single room for one night on the base of HB in Kocani; A hall with appropriate audio equipment for conducting of Training for approximately 20 people; one daily coffee breaks (complete coffee, mineral water, juice and cookies) for all participants in workshops (20 participants) and catering – lunch with included one non-alcoholic beverages per participant.

Activity 4.2.2.3 Organization of workshops

The Contractor for organization of four workshops ( one day each) in Stip should provide:

Hall for conducting each workshop for approximately 30 people;

one daily coffee breaks (complete coffee, mineral water, juice and cookies) for 30 participants.

For the exact date of holding of each of the above-mentioned events the respective Contractor will be informed at least 30 days before the planned date of holding of event.

# LOT 3 Organization of campaign and visibility materials

### Activity 4.2.3.1 Design, preparation and printing of promotional materials and consumables

The Consultant should support the Centre for Development of the East Planning Region in overall process of implementation of the project trough design, printing and delivery of consumables for project events and project promotional materials. Following materials and consumables should be designed, printed and delivered:

Promotional materials:

400 Brochures with project info content, 8 A5 pages printed in color with the content prepared by the Contracting Authority

400 Leaflets two A5 pages with the project info content prepared by the Contracting Authority

400 Folders with color cover

- Notepads, A5 format with printed color cover on 300gr/m2 paper and metal wire binding

- Pens with printed logo of the programme

- USBs (at least 32 GB memory)

- Hats –with printed name of the project and CBC Programme logo in color

400 T-shirts - with printed name of the project and CBC Programme logo in color

400 canvas bags - with printed name of the project and CBC Programme logo in color

3 banners

works info boards (8) - printed sheet metal board A2 form

permanent info boards (6) – printed metal board A1 form, with frame

Consumables:

40 sets of consumables for promotional press conferences (one set include: folder, note book, pen, agenda, project info brochure)

40 sets of consumables for closing press conferences (one set include: folder, note book, pen, agenda, project info brochure)

by 20 sets of consumables for each Training (4) (one set include: folder, notebook, pen, agenda and presentations and exercise materials). Total 80 sets

30 sets of consumables for each Workshop (4) in Shtip (one set include: folder, notebook, pen, agenda, presentations and exercise materials)

Contracting Authority is obliged to present in Macedonian language the necessary texts. All aspects of preparation of materials e.g. design, colour and text translations are subject of prior approval by the Contracting Authority.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

Activity 4.2.3.2 Design, preparation and printing of promotional materials and consumables

Consultant should support Center in the implementation of project through design and implementation od  Public Campaign. Aim of public awareness campaigns is to achieve long-term lasting behavioral changes of the local population. Campaign should use standard methods (billboards, brochure, audio and video spots, campaign events, presentations) and multimedia platforms. The planned public awareness campaign should be implemented in a few basic steps:

Design and elaboration of printed informational materials - brochures;

Publications in local and regional media;

Creation of videos and audio clip focused on implementing green infrastructure related measures.

Several ways of communication should be served like: dissemination of printed campaign promotion materials; communication and information through social and mass-media; using informal networks for information dissemination, Campaign advertising, Using new media channels to spread messages (you tube, facebook, twitter), Broadcasting of audio and video spots, billboards.

Brochure should be prepared and design by the Consultant.

Campaign should be implemented in Shtip. All materials should be prepared on three languages (Macedonian, Bulgarian and English).

Following materials will be prepared:

- One video spot in a short (30 seconds) and long version (2 minutes)

- Audio spot (30 sec)

- Publication of audio spot on radio (100 publication on local and/or regional radios in period of two months)

- Publication of short video on Tv (local and/or regional -20 publications)

- Publication of video on on-line media (for period of one month) on 3 on-line media

- brochure (300)

- leaflet (300)

- canvas bag (printed) (300)

- cap (printed) (300)

- design for billboard and rent of 4 billboards for two months in Stip

- 6 permanent tables erected on the locations of the green infrastructure interventions

All aspects of preparation of materials e.g. design, colour and text translations are subject of prior approval by the Contracting Authority.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

## Project management

### Responsible body

The Contracting Authority for the contract is:

Center for development of the East planning region

Str. Vanco Prke 119, second floor, 2000 Stip, North Macedonia CDEPR is responsible for the implementation of the project. Any issue regarding this project will be addressed to CDEPR.

### Management structure

The Contracting Authority is Centеr for development of the East planning region, Republic of North Macedonia and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by Centеr for development of the East planning region, Project office – which is responsible for implementation of project “Transforming of urban sites with Green infrastructures “financed under Bulgaria – North Macedonia IPA Cross-border Programme.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant/s in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

Stip, East planning region of North Macedonia

## Start date & period of implementation of tasks

The intended start date is 11.11.2024 and the period of implementation of the contract will be 25 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.<

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in Macedonian in one original and two copies:

Draft final report of maximum 5 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

LOT 1 Consultancy

- Developed Green Infrastructure Strategy (2025 – 2035)

- Formulated of Action plan (2025 – 2030) for green infrastructure for Shtip

- Developed of Joint green cities concept for Shtip and Gotse Delchev

- Provided of expert for capacity building programme

LOT 2 Project events organization

- Organized two press conferences

- Organized 4 trainings

- Organized 4 workshops

LOT 3 Organization of campaign and visibility materials

Designed, Printed and delivered following material:

- 400 Brochures

- Leaflets

- Folders

- Notepads

- Pens

- USBs

- 400 Hats

- 400 T-shirts

- 400 canvas bags

- 3 banners

- works info boards (8)

- permanent info boards (6)

- 190 sets of consumables for press conferences and trainings

Implemented public awareness campaign and:

- produced One video spot in a short (30 seconds) and long version (2 minutes)

- produced Audio spot (30 sec)

- Publicised of audio spot on radio (100 publication on local and/or regional radios in period of two months)

- Publicised of short video on Tv (local and/or regional -20 publications)

- Publicised of video on on-line media (for period of one month) on 3 on-line media

- Designed and printed brochure (300)

- Designed and printed leaflet (300)

- Designed and printed canvas bag (printed) (300)

- Designed and printed cap (printed) (300)

- Designed and printed design for billboard and rent of 4 billboards for two months in Stip

- 6 permanent tables erected on the locations of the green infrastructure interventions