ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Ministry of Interior of the Republic of Serbia

## Country background

Serbia is disaster-prone country, subject to a wide variety of natural disasters, including floods, forest fires, landslides and earthquakes. These disasters, especially weather-related events, are likely to increase in terms of numbers and severity due to climate change (rising temperatures, increasing intensity and frequency of heavy rainfalls, extreme events, storms, floods and droughts).

Having in mind the global climate changes and the fact that the region of South Eastern Europe is prone to different kind of natural disasters, the main objective of the Sector for Emergency management is to further develop the service and build capacities for performing the activities in the field of disaster risk reduction, prompt first response in case of emergency and mitigation and/or Current situation in the sector.

## Current situation in the sector

The mission of the Sector for Emergency Management of the Ministry of Interior (SEM, MoI RS) is to build, maintain and improve the ability of the whole nation to reduce risks, respond to emergencies and disasters, and mitigate the consequences of various disasters that may hit the country and the region. SEM, MoI RS performs legislative, administrative, organizational and technical, preventive, educational, informative and other activities for the protection of life, health, and property of citizens, the environment, and cultural heritage; its operational structures respond in case of natural and man-made disasters - urban fire, open land fire, technical and technological accidents, hazardous substances accidents, flood, earthquake, landslides, etc, and assist in eliminating consequences of emergency situations and disasters (mitigation and rehabilitation).

The progress in disaster risk management approach on the local level in Republic of Serbia is noticeable after numerous activities implemented jointly with the international partners, however the capacities of the local level for both prevention and response to emergencies (caused either by natural or man-made disasters) are still limited. Therefore, it will be necessary to continue building capacities and strengthening coordination mechanisms for better preparedness for, and response to emergencies (caused by natural or man-made disaster), in order to meet the requirements of the EU concept for the risk management and civil protection.

## Related programmes and other donor activities

This Project is complementary to other national and programmes financed by EU.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

- The project is aiming at ensuring the necessary education and preparation of the population and volunteers for actions in case of disasters in the cross border region, as well as ensuring proper and timely response of the professional teams in case of disasters using different methods for improvement of the capacity. Well-coordinated professional teams and volunteers in cross border region and properly educated local population will increase local response capacity and disaster resilience.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

- Successful implementation of project activities which is related to organization of joint events in Serbia

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Accommodation, conference room and catering services for participants during the project events were organized

- Two specialized trainings for rescue in tunnels were organized

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

n/a

## Risks

n/a

# SCOPE OF THE WORK

## General

### Description of the assignment

- The contract should support Ministry of Interior of the Republic of Serbia, Sector for Emergency Management in the process of implementation of project activities under the project „Preparation of the population for actions in case of disasters and improvement of the capacity of the professional teams for response in case of emergency situations within the cross-border region”, financed under INTERREG-IPA CBC Bulgaria-Serbia Programme.

- The contractor should provide services related to the organization of accommodation and catering and conference room for participants during the project events, as well as engagement of experts (trainers) who will conduct specialized trainings in the field of rescue in tunnels.

### Geographical area to be covered

Republic of Serbia - Pčinja, Zaječar, Pirot and Nišava districts

### Target groups

Representatives of Sector for Emergency Management, Ministry of Interior of the Republic of Serbia, Directorate General Fire Safety and Civil Protection, Ministry of Interior Republic of Bulgaria, Academy of MoI, Bulgaria, National Association of Volunteers in Republic of

Bulgaria

## Specific work

Activity 1. Organization of catering service for participants on the trainings:

- 3 joint trainings, 4 working days each training, for 22 participants

Location: Zaječar (Premises of Sector for Emergency Management in Zaječar)

- The contractor should provide meals (breakfast, lunch and dinner) for 4 days (approximately 63 breakfasts, 88 lunches and 66 dinners per training), and 2 coffee breaks per day. The meals should be provided in event venue or in the restaurant (max. 500m away from the event venue).

- 3 joint trainings, 4 working days each training, for 22 participants

Location: Vranje (Premises of Sector for Emergency Management in Vranje)

- The contractor should provide meals (breakfast, lunch and dinner) for 4 days (approximately 63 breakfasts, 88 lunches and 66 dinners per training), and 2 coffee breaks per day. The meals should be provided in event venue or in the restaurant (max. 500m away from the event venue).

- 1 training “Best practice for the rescue interventions in tunnels”, 3 working days, for 33 participants

Location: Niš (Hotel)

- The contractor should provide meals (lunch and dinner) for 3 days (approximately 99 lunches and 66 dinners), and 2 coffee breaks per day.

- 1 training for instructors for the rescue interventions in tunnels, 5 days for 11 participants

Location: Vranje (Hotel)

- The contractor should provide meals (lunch and dinner) for 4 days (approximately 55 lunches and 44 dinners), and 2 coffee breaks per day.

Catering service include:

- Breakfast with refreshment (coffee, water and soft drinks).

- The lunch will include at least the following (per person): main course, salad, bread, dessert, water, soft drink and coffee/tea.

- The dinner will include at least the following (per person): cold starter, main course, bread, salad, dessert, water, soft drink, and coffee/tea.

- Coffee breaks will includes sufficient amount of sparkling and still mineral water, soft drink, coffee/tea with milk and sugar, snacks or cookies.

All meals have to be good quality and standard quantity. If some participants have special dietary needs, Contractor will be inform about it 2 days before events.

Activity 2: Organization of accommodation for participants on the trainings:

- 3 joint trainings, 4 working days (3 nights) each training, for 1 person

Location: Zajecar

- The contractor should provide accommodation for three (3) nights per training, in a single rooms, in at least a 3 stars hotel (in a total – 9 nights in hotel)

- 3 joint trainings, 4 working days (3 nights) each training, for 1 person

Location: Vranje

- The contractor should provide accommodation for three (3) nights per training, in a single rooms, in at least a 3 stars hotel (in a total - 9 nights in hotel)

- 1 training “Best practice for the rescue interventions in tunnels”, 3 working days (2 nights), for 33 participants

Location: Niš

- The contractor should provide accommodation for two (2) nights with breakfast for 33 participants in a single rooms, in at least a 3 stars hotel (in a total - 66 nights with breakfast in hotel).

- The contractor should provide conference room for training “Best practice for the rescue interventions” for 3 days, approximately 7 hours per day, with the capacity for at least 35 participants.

- 1 training for instructors for the rescue interventions in tunnels, 5 days (4 nights) for 11 participants

Location: Vranje

- The contractor should provide accommodation for four (4) nights with breakfast for 11 participants in a single rooms, in at least a 3 stars hotel (in a total – 44 nights in hotel).

- The contractor should provide conference room for 2 days, approximately 7 hours per day, with the capacity for at least for at least 11 participants.

The accommodation should include breakfast with refreshment (coffee, water and soft drinks).

All hotels should not be more than 500 m away from the event venue (conference room), and it should have free Wi-Fi Internet and parking for participants.

The conference room must be equipped with the necessary technical equipment (air conditioning, internet connection, sound system, video projector, laptop, projection screen, flipchart). The Contractor should arrange the room according to instructions given by the contracting authority.

Activity 3. Organization of catering service for promotional event

            - 1 press conference, 1 day duration (approximately 4 hours), for 30 participants

Location: Pirot

- The contractor should provide 1 coffee break (before the event) for 30 people. It should include sufficient amount of sparkling and still mineral water, soft drink, coffee/tea with milk and sugar.

- The contractor should serve catering as a buffet and it should include at least the following: appetizer, main course (meat and vegetarian), salad, bread, dessert, and beverages.

- The contractor should provide a conference room for approximately 4 hours. The conference room must be equipped with the necessary technical equipment (air conditioning, internet connection, sound system, video projector, laptop, projection screen, flipchart). The Contractor should arrange the room according to instructions given by the contracting authority.

Activity 4. Organization of specialized trainings for the rescue interventions in tunnels

The contractor should engage three external experts with professional experience in emergency response in tunnels.

The contractor will cover all costs related to the engagement of experts – preparation costs, expert’s fees and transportation costs to the training venue in Serbia.

- Training “Best practice for the rescue interventions in tunnels” will be held in Niš, Serbia, and will cover different topics: specifics of emergencies in tunnels, characteristics of specialized equipment, safety considerations and protective measures, case study from real event.

- Total number of participants is 33 (30 professional fire-fighters from Serbia and Bulgaria, 2 experts and 1 translator )

- Training will last 3 days (approximately 7 hours per day)

- Training will be conducted by 2 experienced lecturers/experts:

- Key expert for the training “Best practice for the rescue interventions in tunnels”

- Key expert for the traffic infrastructure

- Training for instructors for the rescue interventions in tunnels will be held in Vranje, Serbia, and will refer to the preparation of SEM MOI representatives for leading tunnel rescue teams and specialization for further transfer of knowledge through training for instructors.

- Total number of participants is 11 (7 specialist and leaders of emergency actions at a higher level, 3 experts and 1 translator)

- Training will last 5 days (2 days of theoretical classes and 3 days of practical exercises- simulation, approximately 7 hours per day)

- Training will be conducted by 3 experienced lecturers/experts with adequate experience and backgrounds

- Key expert for the training “Best practice for the rescue interventions in tunnels”

- Key expert for the traffic infrastructure

- Key expert for field exercises

- Key experts should prepared detailed plan and program of the training which will be approved by Contracting authority. Training program should be adapted to potential risks in the target territory, as well as to the level of knowledge and needs of the training participants.

- Key experts should provide all necessary working materials and instructions, as well as equipment and tools for practical exercises – simulation (should be included in a total price).

## Project management

### Responsible body

Sector for Emergency Management, Ministry of Interior of the Republic of Serbia.

### Management structure

The responsible persons for implementation of the tasks related to this contract, in the Contracting Authority are Legal representative-Head of Sector for Emergency Management and Project Coordinator.

### Facilities to be provided by the contracting authority and/or other parties

n/a

# LOGISTICS AND TIMING

## Location

Tasks related to this contract will be implemented in Republic of Serbia: Zaječar, Pčinja, Pirot and Nišava districts.

## Start date & period of implementation of tasks

The intended start date is 31.01.2025 and the period of implementation of the contract will be 13 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts is defined and must submit CV and signed statement of exclusivity and availability. Experts who have a crucial role in implementing the contract are referred to as key experts.

The profile of the key expert for this contract is as follows:

- Key expert for the training “Best practice for the rescue interventions in tunnels”

Qualifications and skills

- University degree in Technical, Social or Natural Science (preferable Master degree, or equivalent)

- Proficiency in English

- Very good communication, presentation and facilitation skills is an asset

General professional experience

- A minimum 15 years of relevant experience in the field of disaster management

- Experience or education in the field of traffic infrastructure, critical infrastructure, CBRN is an advance

Specific professional experience

- Professional experience in the field of rescue interventions in tunnels

- Experience in coordination of training programs, teaching, and knowledge transfer (theoretical and practical)

- Familiarity with the EU Civil Protection Mechanism is an advantage

- Key expert for the traffic infrastructure

Qualifications and skills

- University degree (preferable Faculty of Transport and Traffic Engineering)

- Very good communication, presentation and facilitation skills is an asset

- Good English skills

General professional experience

- A minimum 5 years of relevant experience in the field of road/traffic safety

- Familiar with of traffic infrastructure in the Republic of Serbia (preferable)

Specific professional experience

- Professional experience in the field of rescue interventions in tunnels

- Experience in coordination of training programs, teaching, and knowledge transfer (theoretical and practical)

- Key expert for field exercises

Qualifications and skills

- Min. High school degree

- Good communication skills

- Knowledge of Serbian language (preferable)

General professional experience

- A minimum 5 years of relevant experience in the field of disaster management

Specific professional experience

- Professional experience in the field of search and rescue from the ruins, traffic and CBRN accident interventions

- Experience in coordination of training programs and field exercises

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and 2 copies:

- Interim report shall be submitted at the end of 6th month. The approval of interim reports will be the basis for issuing respective interim payments as indicated in the Special Conditions. The interim reports must be provided along with the corresponding proforma invoice.

- Final report of maximum 6 pages (main text, excluding annexes) shall be submitted at the end of the period of implementation of tasks. The approval of the final report by the Contracting Authority will be the basis for issuing final payment as indicated in the Special Conditions.

## Submission and approval of reports

The report referred to above must be submitted to the project coordinator. The project coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Services provided in timely, quality and quantity manor, as required in these Terms of Reference

## Special requirements

n/a